## Sheet2
Table 2.1: Quantum of Work Approved vs Achieved
Sl. no | Item of work | Quantum approved | Quantum achieved | Remarks
Annexures/Plates
1 | Geological mapping (on 1:12500) | 72.14 sq. km | 72.14 sq. km | COMPLETED | Plate-I (A) & I(B)
2 | Bedrock sampling | 50 Nos. | 84 Nos. | Approval was accorded by NMEDT, TCC for additional quantum
3 | Geophysical survey (SP survey) | 5 L.km | 5 L.km | COMPLETED
4 | Technological Survey
| (a) Pitting (where BRS is not available) | 50 cu.m | 27 cu.m | Approval was accorded by NMEDT, TCC for additional quantum of trench | Plate-X(B)
| (b) Trenching | 100 cu.m | 123 cu.m |  | Plate-X(A)
| (c) Drilling | 500 m | 462 m | COMPLETED | Plate-IX
5 | Laboratory studies
| (a) Proximate analysis for graphite (BRS: 50; PT:100; BH Core: 100) | 250 Nos. | 375 Nos. | Approval was accorded by NMEDT, TCC for additional quantum
|  |  | (BRS: 84; PT: 66; Core: 225) |  | Annexure-I, II & X
| (a) Proximate analysis for graphite 10% external check | 25 Nos. | 25 Nos. | Analysis report has been received for all samples
Annexure-XI
| (c) Analysis for associated REE + Vanadium (ICPMS 14 elements) | 20 Nos. | 20 Nos. | Analysis report has been received for all samples
Annexure-XII
| (d) Petrochemical studies (PCS) | 10 Nos. | 10 Nos. | Analysis report has been received for all samples | Annexure-XIII
6 | Petrographic studies
| a) Preparation of thin sections | 10 Nos. | 10 Nos. | COMPLETED
| b) Study of thin section | 10 Nos. | 10 Nos. | COMPLETED
| c) Digital photographs | 10 Nos. | 10 Nos. | COMPLETED