## Table No - 2.1
Sl. No | Item of Work | Unit | Target | Achievement
1 | Geological Mapping (on 1:12,500 Scale) | Sq. km | 6.12 | 6.12
2 | Exploratory Mining
a | Excavation of pits (20 no’s), size: 1*1*1 | Cu.m | 20 | 20
| Pit samples collected | Nos | 20 | 20
b | Excavation of Trenches (5 no’s), Size 10*1*1 | Cu.m | 50 | 50
| Trench samples (14*5=70) collected | Nos | 70 | 70
3 | DGPS survey (6 block boundary points & 4 Borehole points) | points | 10 | 10
4 | Scout drilling: 4 boreholes of 30m depth each (4*30=120m) | meters | 120 | 101
a | Construction of borehole pillar | no’s | 4 | 4
b | Compensation for 4 Bhs | no’s | 4 | -
c | Drill core preservation in GI boxes | meters | 120 | 96
5 | Laboratory Studies
| Major oxides by XRF (Trench-70, pit-20, BH-40 =130 + 13 check samples) | Nos | 143 | (92+36) +(10+4) check =142
| REE 14 Elements by ICPMS 33+ 3 check | Nos | 36 | (15+15) +(2+2) check=34
| Combined determination of THA, MHA and Reactive silica | Nos | 4 | 2
7 | Preparation of polished thin sections | Nos | 10 | 5
8 | Complete petrographic//ore2qw3456790- [21-microscopic / mineragraphic studies | ` | 10 | 5
9 | XRD Mineral phase analysis | Nos | 4 | 3
10 | Report Preparation (5 Hard copies with a soft copy) | Nos. | 1 | 1

## Table No - 2.2
Sr. No | Work component | Agency
1 | Large scale Geological mapping (1:12,500 scale) | CMT (In house)
2 | Pitting, trenching & drilling | CMT (In house)
3 | DGPS Survey | CMT (In house)
4 | Chemical Analysis | Lucid laboratories Pvt Ltd, Hyderabad (NABL accredited lab))
5 | XRD and check sample analysis | Shiva Analyticals India Pvt Ltd, Bengaluru (NABL accredited lab)
6 | Polished thin section & complete petrographic studies. | Petrology division, GSI, Southern Region Hyderabad

## Table No - 2.3
Details of Personnel Associated with the exploration work are as under
1 | Overall Planning, Co-ordination & Overall supervision | : | S.Rama Murthy (Retd Dirctor, GSI), Technical area Expert (In house)
|  | : | S.Uma Maheswara rao (Retd Scientist, MECL), Technical Area Expert (In house)
3 | Project management & Field Operation | : | S.Rama murthy, Technical area Expert (In house)
S.Uma maheswara rao, Technical Area Expert (In house)
|  | : | B. Mahesh, Geologist (In house Team Member)
5 | Chemical Laboratory | : | LUCID Laboratory Private Limited, Hyderabad, (NABL Accredited laboratory)
6 | Petrological studies | : | Petrology Divn., Geological Survey of India, Southern Region, Hyderabad
8 | Data Processing & Documentation | : | Shri S.Rama murthy, Technical area Expert (In house)
|  | : | S.Uma maheswara rao, Technical Area Expert (In house)
Mr B. Mahesh, Geologist (In house Team Member)
9 | Reprography & Printing | : | Mr. B. Mahesh Geologist (In house Team Member)
|  | : | Mr. V. Siva Kumar, Geologist (In house Team Member)

## Table No - 3.1
Details of coordinates and elevation of 6 cardinal points as determined by DGPS Survey
Cardinal Points | Geographic Coordinate System in Degree Decimal |  | UTM |  |  | Area in Sq. Km
| (WGS 1984) |  | (WGS 1984, Zone 42N)
| Latitude (N) | Longitude (E) | Elevation (m) | Northing (m) | Easting
(m)
A | 23.2443 | 69.8164 | 122.97 | 2570797.727 | 583516.695 | 6.12
B | 23.2436 | 69.7858 | 116.156 | 2570709.109 | 580384.345
C | 23.26 | 69.7842 | 121.514 | 2572513.684 | 580215.033
D | 23.2614 | 69.8112 | 119.173 | 2572687.425 | 582969.005
E | 23.2638 | 69.8161 | 120.549 | 2572956.616 | 583470.469
F | 23.2643 | 69.8112 | 122.99 | 2573009.696 | 582967.814

## Table No - 5.1
Generalised stratigraphic succession of Kachchh mainland basin
Age | Group | Sub-group | Formation | Lithology
Holocene |  |  | Rann | Aeolian sand, clay, marl
Pliocene |  |  | Sandhan | Calcarenite, conglomerate, sandstone & clay
Miocene |  |  | Gaj | Fossiliferous limestone, marl, clay
Oligo-Miocene |  |  | Khari Nadi | Variegated Gups shale, siltstone, fossil, marl
Palaeocene |  |  | Matanomadh | Laterite/ bauxite with clay
Late Cretaceous-Palaeocene | Kachchh | Deccan trap | Anjar volcanics | Basalt (unclassified)
Early Cretaceous |  |  | Bhuj | Ferruginous, feldspathic sandstone, siltstone, shale, clay, plant fossils
Late Jurassic to early Cretaceous |  |  | Katrol (Jhuran) | Feldspathic sandstone, shale with ammonite, calc sandstone, limestone, siltstone
Middle to late Jurassic |  |  | Chari (Jhuran) | Calc gritty sandstone, gypseous shale, marl, Oolitic Limestone
Middle Jurassic |  |  | Pachcham (Jhurio) | Shale with micaceous sandstone, limestone
Basement not exposed

## Table No - 6.1
Bhuj Formation: major oxides, Vanadium, Gallium, TREE
Oxide/element | pits |  |  | Trenches
| Min | Max | Mean | Min | Max | Mean
SiO2% | 37.04 | 86.1 | 51.03 | 31.01 | 43.23 | 36.65
Al2O3% | 0.1 | 39.34 | 21.99 | 14.95 | 30.8 | 22.31
Fe2O3% | 1.21 | 24.19 | 9.45 | 3.07 | 32.78 | 16.6
TiO2% | 0.52 | 8.35 | 2.25 | 1.69 | 9.59 | 5.21
Vanadium(ppm) | 53.4 | 502 | 197.62 | 80.4 | 502.08 | 274.51
Pit & trench samples
Gallium(ppm) | Min: 13.1 |  | Max:50.85 |  | Mean: 30.32
Total REE ppm | Min: 217.29 |  | Max:1469.62 |  | Mean: 679.43
(TREE+Sc+Y) ppm | Min: 241.5 |  | Max:1555.25 |  | Mean: 733.17

## Table No - 6.2
Sandhan Formation: major oxides, vanadium, Gallium, TREE
Oxide/element | pits |  |  | Trenches
| Min | Max | Mean | Min | Max | Mean
SiO2% | 43 | 61.08 | 53.61 | 24.06 | 87.75 | 52.48
Al2O3% | 15.16 | 35.15 | 22.38 | 0.24 | 46.01 | 21.87
Fe2O3% | 0.99 | 8.85 | 5.7 | 1.02 | 120.61 | 8
TiO2% | 1.73 | 3.85 | 2.74 | 0.79 | 4.56 | 2.37
Vanadium(ppm) | 115.1 | 198.93 | 163.24 | 32.5 | 444 | 182.11
Pit & trench samples
Gallium(ppm) | Min: 14.68 |  | Max:41.48 |  | Mean: 28.43
Total REE ppm | Min: 311.00 |  | Max:748.57 |  | Mean: 520.38
(TREE+Sc+Y) ppm | Min: 375.13 |  | Max:795.15 |  | Mean: 570.12

## Table No - 6.3
The location of Pits (measured by GPS)
Sr No | Pit No | Coordinate in Degree Decimal Datum WGS-1984 |  | No of samples collected
|  | Longitude (E) | Latitude (N)
1 | P1/LB/2025 | 69.8147 | 23.2529 | 1
2 | P2/LB/2025 | 69.814 | 23.2558 | 1
3 | P3/LB/2025 | 69.8161 | 23.2537 | 1
4 | P4/LB/2025 | 69.7905 | 23.2553 | 1
5 | P5/LB/2025 | 69.7921 | 23.2534 | 1
6 | P6/LB/2025 | 69.7889 | 23.2543 | 1
7 | P7/LB/2025 | 69.7881 | 23.2559 | 1
8 | P8/LB/2025 | 69.7876 | 23.2569 | 1
9 | P9/LB/2025 | 69.7849 | 23.2587 | 1
2026-11-10 | P10A/LB/2025 | 69.7878 | 23.2556 | 2
P10B/LB/2025
12 | P11/LB/2025 | 69.7867 | 23.2532 | 1
13 | P12/LB/2025 | 69.7921 | 23.2482 | 1
14 | P13/LB/2025 | 69.7852 | 23.2518 | 1
15 | P14/LB/2025 | 69.7952 | 23.2535 | 1
16 | P15/LB/2025 | 69.7854 | 23.2479 | 1
17 | P16/LB/2025 | 69.8129 | 23.254 | 1
18 | P17/LB/2025 | 69.8097 | 23.257 | 1
19 | P18/LB/2025 | 69.8075 | 23.2557 | 1
20 | P19/LB/2025 | 69.8024 | 23.2575 | 1
21 | P20/LB/2025 | 69.806 | 23.2585 | 1
22 | BRS-1 | 69.8003 | 23.2558 | 1

## Table No - 6.4
The location of the trenches is mentioned below
Sr No | Trench No | Coordinate in Degree Decimal
Datum WGS-1984
|  | Longitude (E) | Latitude(N)
1 | T1/LB/2025 | 69.7906 | 23.2502
2 | T2/LB/2025 | 69.8008 | 23.2555
3 | T3/LB/2025 | 69.7873 | 23.2443
4 | T4/LB/2025 | 69.8097 | 23.2583
5 | T5/LB/2025 | 69.8041 | 23.248

## Table No - 6.5
Summary of major oxide values (pit &trench samples) of Bhuj formation
Oxides (%)/ | Minimum | Maximum | Mean
Element (ppm) | value | values | value
SiO2 (%) | 31.01 | 86.1 | 42.08
Al2O3(%) | 0.1 | 39.34 | 22.22
Fe2O3(%) | 1.21 | 32.78 | 13.92
MnO (%) | 0.01 | 0.16 | 0.02
MgO (%) | 0.01 | 0.93 | 0.27
CaO (%) | 0.13 | 15.68 | 3.47
Na2O (%) | 0.04 | 0.39 | 0.14
K2O (%) | 0 | 0.62 | 0.2
TiO2(%) | 0.52 | 9.59 | 4.07
P2O5(%) | 0.02 | 0.49 | 0.18
LOI (%) | 1.63 | 17.7 | 13.23
V(ppm) | 53.4 | 502.08 | 243.98

## Table No - 6.6
Summary of REE and Gallium values of (pit & trench samples) Bhuj Formation
Bhuj Formation
Element (ppm) | min | max | Average
Lanthanum (La) | 40.65 | 217.03 | 93.62
Cerium (Ce) | 70.6 | 395.38 | 201.16
Praseodymium (Pr) | 9.55 | 84.3 | 40.46
Neodymium (Nd) | 60.5 | 565.65 | 252.03
Promethium (Pm) | - | - | -
Samarium (Sm) | 5.83 | 64.88 | 23.03
Europium (Eu) | 1.18 | 13.6 | 5.04
Gadolinium (Gd) | 5.75 | 68.95 | 30.06
Terbium (Tb) | 1.43 | 1.43 | 1.43
Dysprosium (Dy) | 2.13 | 21.15 | 8.69
Holmium (Ho) | <1.0 | <1.0 | <1.0
Erbium (Er) | 3.63 | 46.18 | 17.54
Thulium (Tm) | <1.0 | <1.0 | <1.0
Ytterbium (Yb) | 1.73 | 12.98 | 5.27
Lutetium (Lu) | 1.1 | 5.43 | 2.95
Total REE | 217.29 | 1469.62 | 679.43
Scandium (Sc) | 10.45 | 49.1 | 23.48
Yttrium(Y) | 13.48 | 48.7 | 30.25
Total (REE +Sc+Y) | 241.5 | 1555.25 | 733.18
Gallium (Ga) | 13.1 | 50.85 | 30.32
Uranium (U) | 32.8 | 260.18 | 80.44
Thorium (Th) | 55.65 | 208.45 | 125.47

## Table No - 6.7
Summary of major oxidex (pit & trench samples) of Sandhan formation
Oxides (%)/ | Minimum | Maximum | Mean
Element (ppm) | value | values | value
SiO2 (%) | 24.06 | 87.75 | 52.55
Al2O3(%) | 0.24 | 46.01 | 21.91
Fe2O3(%) | 0.99 | 20.61 | 7.85
MnO (%) | 0.01 | 0.18 | 0.06
MgO (%) | 0.06 | 1.93 | 0.76
CaO (%) | 0.13 | 3.92 | 0.96
Na2O (%) | 0.08 | 1.5 | 0.49
K2O (%) | 0.02 | 7.52 | 0.46
TiO2(%) | 0.79 | 4.56 | 2.4
P2O5(%) | 0.04 | 0.69 | 0.11
LOI (%) | 3.21 | 22.29 | 12.29
V(ppm) | 32.5 | 444 | 180.86

## Table No - 6.8
Summarized table showing range of REE & Ga in Sandhan formation
REE | Minimum value(ppm) | Maximum value (ppm) | Mean Value (ppm)
(ppm)
Lanthanum (La) | 38.8 | 113.15 | 77.71
Cerium (Ce) | 70.43 | 224.35 | 165.42
Praseodymium (Pr) | 23.53 | 32.15 | 26.3
Neodymium (Nd) | 109.68 | 304.98 | 190.52
Promethium (Pm) | NA | NA | NA
Samarium (Sm) | 10.43 | 19.45 | 14.08
Europium (Eu) | 2.4 | 4.25 | 3.27
Gadolinium (Gd) | 10.88 | 25.15 | 15.82
Terbium (Tb) | <1.0 | <1.0 | <1.0
Dysprosium (Dy) | 4.38 | 9.03 | 7.04
Holmium (Ho) | <1.0 | <1.0 | <1.0
Erbium (Er) | 10.18 | 20.13 | 14.11
Thulium (Tm) | <1.0 | <1.0 | <1.0
Ytterbium (Yb) | 2 | 8.08 | 5.19
Lutetium (Lu) | 1 | 2.75 | 1.88
Total REE | 311 | 748.57 | 520.39
Scandium (Sc) | 16.48 | 28.33 | 20.02
Yttrium(Y) | 12.73 | 47.65 | 29.71
(Total REE+Sc+Y) | 375.13 | 795.15 | 570.12
Gallium (Ga) | 14.68 | 41.48 | 28.43
Uranium (U) | 65.18 | 65.18 | 65.18
Thorium (Th) | 43 | 148.53 | 83.97

## Table No - 6.9
Analysis of Major oxides in Matanomadh formation
Oxides (%)/ | Values
Element (ppm)
SiO2 (%) | 33.99
Al2O3(%) | 28.59
Fe2O3(%) | 20.23
MnO (%) | 0.05
MgO (%) | 0.37
CaO (%) | 1.01
Na2O (%) | 0.38
K2O (%) | 0.55
TiO2(%) | 1.48
P2O5(%) | 0.18
LOI (%) | 12.96
V(ppm) | 199.78
Total REE (ppm) | 504.64
Scandium | 21.75
Yitrium | 27.83
Total REE + (Sc+Y) | 554.22
Gallium(ppm) | 41.73
Uranium (ppm) | 140.63
Thorium (ppm) | 133.6

## Table No - 6.10
Analysis of Major Oxides in Gaj formation
Oxides (%)/ | Minimum
Element (ppm) | value
SiO2 (%) | 61.8
Al2O3(%) | 16.31
Fe2O3(%) | 8.63
MnO (%) | 0.03
MgO (%) | 0.78
CaO (%) | 0.74
Na2O (%) | 0.18
K2O (%) | 0.76
TiO2(%) | 1.69
P2O5(%) | 0.09
LOI (%) | 8.72
V(ppm) | 93.7

## Table No - 6.11
RL, Coordinates of Cardinal points, boreholes and Temporary bench marks in Lakhond Area, District: Kachchh, Gujarat (as Determined by DGPS Survey)
Cardinal Points | Geographic Coordinate System in Degree decimal (WGS-84) |  | UTM (WGS-84, Zone 42N) |  |  | Area
| Latitude (N) | Longitude (E) | Reduced level (m) | Northing (m) | Easting (m) | (Sq. Km)
A | 23.2443 | 69.8164 | 122.97 | 2570797.727 | 583516.695 | 6.21
B | 23.2436 | 69.7858 | 116.156 | 2570709.109 | 580384.345
C | 23.26 | 69.7842 | 121.514 | 2572513.684 | 580215.033
D | 23.2614 | 69.8112 | 119.173 | 2572687.425 | 582969.005
E | 23.2638 | 69.8161 | 120.549 | 2572956.616 | 583470.469
F | 23.2643 | 69.8112 | 122.99 | 2573009.696 | 582967.814
Borehole points
LKD-BH-01 | 23.2446 | 69.7874 | 113.219 | 2570816.417 | 580548.359
LKD-BH-02 | 23.2573 | 69.8101 | 116.957 | 2572231.69 | 582863.095
LKD-BH-03 | 23.2558 | 69.8006 | 118.23 | 2572067.162 | 581892.377
LKD-BH-04 | 23.2544 | 69.7889 | 118.228 | 2571897.891 | 580701.485
Temporary bench marks
LKD-TBM-1 | 23.2535 | 69.7922 | 117.079 | 2571798.84 | 581031.969
LKD-TBM-2 | 23.2533 | 69.7924 | 115.973 | 2571785.264 | 581055.727

## Table No - 6.12
XRD analytical results of samples
Sl. No | Sample No. | Mineral Phases | Approximate %
1 | P27/LB/2025 | Kaolinite | 40.06
| (Original no: P17/LB/2025) | Hematite | 1.85
|  | Goethite | 24.1
|  | M-silicate | 0.98
2 | T13/LB/2025/03 | Kaolinite | 35.37
| (Original no: T3/LB/2025/03) | Gibbsite | 39.85
|  | Ilmenite | 2.16
3 | T14/RB/2025/05 | Kaolinite | 31.05
| (Original no: T4/LB/2025/05) | Goethite | 21.69
|  | Hematite | 5.91
|  | Calcite | 5.53
|  | Quratz | 2.95
|  | Cristobalite | 2.94

## Table No - 9.1
showing Coordinates, RL, Total depth, core recovery date of commencement and completion
Bore Hole No. | Geographic Coordinate System in Degree Minutes Seconds |  | Geographic Coordinate System in Degree Decimal |  | RL Collar (m) | Core recovery (%) | Date of Commencement | Date of Completion | Total depth(m)
| (WGS 1984) |  | (WGS 1984)
| Latitude (DMS) | Longitude (DMS) | Latitude (DD) | Longitude (DD)
LKD BH - 1 | 23°14'40.5810" | 69°47'14.5971" | 23.2446058° | 69.7873881° | 113.219 | 63% | 19.07.2025 | 24.07.2025 | 30
LKD BH - 2 | 23°15'26.1860" | 69°48'36.3273" | 23.2572739° | 69.8100909° | 116.957 | 85% | 25.07.2025 | 02.08.2025 | 30
LKD BH - 3 | 23°15'21.0114" | 69°48'02.1340" | 23.2558365° | 69.8005928° | 118.23 | 90% | 17.09.2025 | 19.09.2025 | 30
LKD BH - 4 | 23015’15.7195” | 69°47’20.1922” | 23.2543665° | 69.7889423° | 118.228 | 93% | 20.09.2025 | 21.09.2025 | 11

## Table No - 9.2
Major oxides and Total REE in BH - 1
LKD - BH - 01
Oxides/element | Minimum | Maximum | Mean
SiO2 % | 34.26 | 67.34 | 47.14
Al2O3 % | 16.39 | 36.82 | 29
Fe2O3% | 2.2 | 14.69 | 6.85
TiO2% | 1.48 | 5.23 | 3.53
P205% | 0.05 | 0.38 | 0.15
Vanadium(ppm) | 68.6 | 243.7 | 161.03
Gallium (ppm) | 29 | 43.1 | 35
Total REE (ppm) | 278.7 | 623.6 | 448.5
TREE+Sc+Y(ppm) | 307.5 | 661.9 | 480.8

## Table No - 9.3
Major Oxides & Total REE in BH – 02
LKD - BH - 02
Oxides/element | Minimum | Maximum | Mean
SiO2 % | 18.59 | 48.32 | 36.26
Al2O3 % | 8.22 | 28.9 | 16.53
Fe2O3% | 10.43 | 36.93 | 18.73
TiO2% | 2.37 | 9.87 | 5.2
P205% | 0.34 | 1.57 | 0.7
Vanadium(ppm) | 126.3 | 506.7 | 268.7
Gallium (ppm) | 17.9 | 40.9 | 25.3
Total REE (ppm) | 329.9 | 636 | 476.4
TREE+Sc+Y(ppm) | 357.1 | 679.9 | 517.1

## Table No - 9.4
Major Oxides & Total REE in BH - 03
LKD - BH - 03
Oxides/element | Minimum | Maximum | Mean
SiO2 % | 29.33 | 74.43 | 51.87
Al2O3 % | 16.59 | 34.51 | 26.97
Fe2O3% | 1.26 | 25.52 | 7.63
TiO2% | 0.39 | 4.21 | 2.02
P205% | 0.06 | 0.42 | 0.18
Vanadium(ppm) | 34.5 | 898.6 | 331.29
Gallium (ppm) | 20.7 | 46.7 | 32.8
Total REE (ppm) | 421.8 | 1187.5 | 695.5
TREE+Sc+Y(ppm) | 445.6 | 1217.5 | 727.1

## Table No - 9.5
Major Oxides & Total REE in BH - 04
LKD - BH - 04
Oxides/element | Minimum | Maximum | Mean
SiO2 % | 33.55 | 69.34 | 51.33
Al2O3 % | 17.44 | 27.48 | 21.79
Fe2O3% | 3.93 | 10.53 | 7.08
TiO2% | 0.55 | 1.45 | 1.1
P205% | 0.06 | 0.1 | 0.08
Vanadium(ppm) | 95.9 | 366.6 | 178.5
Gallium (ppm) | 14.9 | 31.3 | 20.8
Total REE (ppm) | 226.7 | 504.3 | 399.3
TREE+Sc+Y(ppm) | 243.8 | 528.4 | 421.6

## Table No - 9.6
Summary statistics of the analytical data relevant TREE Characterisation of Bhuj Formation
Parameters | Min | Max | Average
Total LREE | 186.1 | 1143.7 | 508.1
Total HREE | 20.5 | 91.6 | 49
Total REE | 228.2 | 1189.5 | 557
Total REE + SC, Y | 245.3 | 1219.5 | 590
LREE/HREE | 4.5 | 25 | 11.8
LREE (%) | 81.8 | 96.1 | 90.2
HREE (%) | 3.9 | 18.2 | 9.8
%Nd in TREE | 39.3 | 57.7 | 46.8
La/Yb | 6 | 45.7 | 15.5

## Table No - 9.7
Summary statistics of the analytical data relevant to TREE Characterisation of Sandhan formation
Parameters | Sandhan Formation
| Min | Max | Average
Total LREE | 253.5 | 578.9 | 415.325
Total HREE | 22.7 | 46.2 | 35.1
Total REE | 280.7 | 625.1 | 450.4
Total REE + SC, Y | 309.5 | 663.4 | 482.7
LREE/HREE | 9.3 | 14.8 | 12
LREE (%) | 90.3 | 93.7 | 92.1
HREE (%) | 6.3 | 9.7 | 7.9
%Nd in TREE | 35.6 | 48.2 | 41.1
La/Yb | 13 | 35.8 | 24.9

## Table No - 9.8
Statement showing drill core analysis of External check samples for major oxides and their comparison with primary samples of Lakhond area, Kachchh district, Gujarat
S.no | Primary check sample | Sample name | SiO2 | Al2O3 | Fe2O3 | MnO | MgO | CaO | Na2O | K2O | TiO2 | P2O5 | LOI | Remarks
(%)
1 | Primary | D/LKD- BH- 01/05 | 34.26 | 36.82 | 3.01 | 0.01 | 0.29 | 2.13 | 1.25 | 0.34 | 4.5 | 0.12 | 16.79 | Lucid Laboratory
1 | Check | D/LKD-BH-01/61 | 36.23 | 31.35 | 3.26 | 0 | 0.26 | 2.6 | 0.48 | 0.33 | 3.49 | 0.1 | 19.38 | Shiva Analyticals
2 | Primary | D/LKD- BH- 02/02 | 32.6 | 28.9 | 17.64 | 0.05 | 0.4 | 0.72 | 0.96 | 0.01 | 5.35 | 0.59 | 12.29 | Lucid Laboratory
2 | Check | D/LKD-BH-02/62 | 30.55 | 23.66 | 21.91 | <0.05 | 0.52 | 0.92 | 0.21 | <0.05 | 6.12 | 0.83 | 14.76 | Shiva Analyticals
3 | Primary | D/LKD - BH - 03/03 | 46.13 | 34.51 | 1.26 | 0.01 | 0.17 | 1.13 | 0.2 | 0.18 | 4.21 | 0.23 | 11.49 | Lucid Laboratory
3 | Check | D/LKD-BH-03/63 | 57.73 | 23.97 | 1.29 | <0.05 | 0.16 | 1.32 | <0.08 | 0.13 | 3.89 | 0.17 | 10.87 | Shiva Analyticals
4 | Primary | D/LKD - BH - 04/01 | 50.12 | 18.81 | 9.71 | 0.03 | 0.67 | 8.91 | 0.27 | 0.59 | 1.41 | 0.1 | 9.05 | Lucid Laboratory
4 | Check | D/LKD-BH-04/64 | 72.24 | 6.84 | 7.31 | <0.05 | 0.25 | 4.05 | <0.08 | 0.29 | 1.18 | 0.06 | 7.44 | Shiva Analyticals

## Table No - 14.1
Location of villages/ factories/Railway stations/Airport around Lakhond block
Locality | Latitude( N) | Longitude (E)
| (Degree decimal) | (Degree decimal)
Ajrakpur | 23.2335 | 69.7972
Bhuj Airport | 23.2755 | 69.6639
Bhuj city | 23.2426 | 69.6644
Bhuj Railway station | 23.2659 | 69.678
Kukma | 23.2167 | 69.7777
Lakhond | 23.2556 | 69.7762
Padhar | 23.2406 | 69.8244